## Title
Wales Interors
Document Classification | Internal
Document Author | GRC Specialist
Document Owner | CISO
Version | 1
Date | 2025-06-21

## Risk Register
Risk ID | Description | Assets | Threat | Vulnerability | Current Control | Likelihood | Impact | Risk Rating | Mitigation Strategy | Treament Plan | ISO Control | Timeline | Owner
R001 | Breach of data via ERP platform | Customer data, operation desruption | Phishing attack resulting in credential theft | Lack of phishing awareness training and best practices | None | 4 | 4 | 16 | Mitigate | Phishing awareness training and simulation test | 6.3, 6.4, 5.32 | 28 days | IT
R002 | Unauthorized access to data | Design files, contracts, finance data | Unlawful modification or theft of sensitive files | Shared password, ex employees still having access | User access log review | 4 | 4 | 16 | Mitigate | Implement access control | 5.15, 5.18, 5.33, 5.32 | 28 days | IT
R003 | Data breach via third party vendor | Customer data, Design files, contracts, finance data | Supply chain compromise | Lack of third-party vetting or patch delays | Limited contractual controls | 1 | 3 | 3 | Mitigate | prevent over sharing of personal data, Conduct vendor risk assessments and restrict third-party access to least privilege | 5.19, 5.20, 5.22, 5.32, 5.23 | 90 days | IT
R004 | Data loss via natural disaster | ERP | Earthquake and flood | No disaster recovery plan and business continuity plan | None | 1 | 5 | 5 | Mitigate | Review physical resilience and implement data recovery site in safe zone | 7.5, 5.33, 5.32, 5.30 | 90 days | IT
R005 | Shadow IT or malicious mobile apps | Design files, contracts, finance data | Use of unauthorized devices/apps to access company data | Lack of BYOD policies or mobile device management | None | 4 | 5 | 20 | Mitigate | Enforce BYOD and MDM policies | 6.7, 5.32, | 45 days | IT
R006 | Regulatory and Compliance risk | Design files, contracts, finance data, customer data | Non compliance with ISO 27001 and GDPR | No clear policies to meet compliance | None | 2 | 5 | 10 | Mitigate | create compliance policies and controls | 5.36, 5.1, 5.2, 5.4, 5.5 | 90 days | IT
R007 | Insecure cloud configuration | Design files, contracts, finance data | using shared password, publicly exposing data due to misconfiguration | No baseline configuration | None | 2 | 3 | 6 | Mitigate | implement baseline configuration policy | 8.9, 5.14 | 90 days | IT
R008 | ERP development lifecycle | Customer data, Design files, contracts, finance data | Introduction of vulnerabilities in custom ERP through poor app development | insecure ERP app, development and life cycle | None | 3 | 5 | 15 | Mitigate | implement secure design development lifecycle to align with ISO 27001 | 8.2, 8.3, 8.4, 8.25, 8.26, 8.28, 8.29, 8.31, 8.32, 8.33 | Immediate (within 7 days) | IT

## Risk Matrix
To Use The Heat Map 1. Risk Score 1 -5 (Low): Accept the risk and monitor 2. Risk Score 6 - 10 (Moderate): Apply minor controls and monitor 3. Risk Score 11 -15 (High): Requires corrective action and controls should be implemented within 45 days 4. Risk Score 16 -20 (Very High): Implement corrective actions and controls should be implemented within 28 days 5. Risk Score 21 -25 (Critical): Implement corrections action immediately and resovle within 14 days | Likelihood ---------------------- Impact | 5 | 4 | 3 | 2 | 1
| 5 | 25 | 20 | 15 | 10 | 5
| 4 | 20 | 16 | 12 | 8 | 4
| 3 | 15 | 12 | 9 | 6 | 3
| 2 | 10 | 8 | 6 | 4 | 2
| 1 | 5 | 4 | 3 | 2 | 1